## EradicationMeasures
CountryCode | SpeciesId | SpeciesName | StartingDate | EstimatedMeasureDuration | DurationType | EndOfMeasureDate | Title | MeasureDescription | SideEffects | EffectDescription | OverallMeasureCost
FI | R05501 | Elodea nuttallii | 2021-07-09 | 2 | Years | 2023-11-07 | Mechanical/physical methods | Mechanical/physical methods. The distribution and size of the E. nuttallii population in the pond have been evaluated in more details in summer 2021. From the areas, where E. nuttallii occurs, the species will be collected and removed manually by diver. | N/A | The distribution and size of the E. nuttallii population in the pond have been evaluated in summer 2021. The suitable management options and risk of spread to new areas were evaluated. The management of the E. nuttallii has been challenging. The species has not been eradicated in two years, The time period for the management has been too short. The distribution and size of the E. nuttallii population in the pond have been re-evaluated in autumn 2023. | 5000
FI | R05501 | Elodea nuttallii | 2021-07-09 | 2 | Years | 2023-11-07 | Mechanical/physical methods | Mechanical/physical methods. The distribution and size of the E. nuttallii population in the pond have been evaluated in more details in summer 2021. From the areas, where E. nuttallii occurs, the species will be collected and removed manually by diver. | N/A | The distribution and size of the E. nuttallii population in the pond have been evaluated in summer 2021. The suitable management options and risk of spread to new areas were evaluated. The management of the E. nuttallii has been challenging. The species has not been eradicated in two years, The time period for the management has been too short. The distribution and size of the E. nuttallii population in the pond have been re-evaluated in autumn 2023. | 5000
FI | R10652 | Oxyura jamaicensis | 2022-06-16 | 6 | Months | 2023-01-31 | Eradication Oxyura jamaicensis | The duck had left the area before eradication actions could be done. There has been no further sightings of the duck after it left the area. Public awareness will be raised e.g. with press release published by BirdLife Finland | N/A | The one individual of O. jamaicensis left the area before eradication measures could be done. Promoting public awareness is done. | 0
FI | R11034 | Perccottus glenii | 2022-11-15 | 7 | Months | 2023-06-27 | Eradication of Perccottus glenii | Chemical eradication of Perccottus glenii from the pond using rotenone. Appr. 20 individuals were caught with the landing net (15.-16.11.2022). The pond was monitored in 25.11. 2022 and about 20 dead individuals were detected with a drone. In addition, 123 individuals were caught with a landing net and 9 of those were still alive. As an estimate 90% of the population has been destroyed. The pond will be monitored in spring 2023 to evaluate the effectiveness of the treatment on Perccottus glenii population and the impact on non-targeted species. If needed the treatment will be conducted again in spring 2023. Samples of benthic animals were taken in 2022. | Possible negative effects on other fish species (Carassius sp.) and benthic animals | Perccottus glenii was eradicated from the pond using rotenone. In the end of November 2022 approximately 90% of the population had been destroyed. In June 2023 no P. glenii individuals were detected from the pond. The rotenone treatment have had negative effects on other fish species (Carassius sp.) and the impacts on benthic animals will be surveyd in the autumn 2023. | 12000
FI | R11034 | Perccottus glenii | 2022-11-15 | 7 | Months | 2023-06-27 | Eradication of Perccottus glenii | Chemical eradication of Perccottus glenii from the pond using rotenone. Appr. 20 individuals were caught with the landing net (15.-16.11.2022). The pond was monitored in 25.11. 2022 and about 20 dead individuals were detected with a drone. In addition, 123 individuals were caught with a landing net and 9 of those were still alive. As an estimate 90% of the population has been destroyed. The pond will be monitored in spring 2023 to evaluate the effectiveness of the treatment on Perccottus glenii population and the impact on non-targeted species. If needed the treatment will be conducted again in spring 2023. Samples of benthic animals were taken in 2022. | Possible negative effects on other fish species (Carassius sp.) and benthic animals | Perccottus glenii was eradicated from the pond using rotenone. In the end of November 2022 approximately 90% of the population had been destroyed. In June 2023 no P. glenii individuals were detected from the pond. The rotenone treatment have had negative effects on other fish species (Carassius sp.) and the impacts on benthic animals will be surveyd in the autumn 2023. | 12000